## Sheet1
Comment | Sheet | Question/Comment | Response
1 | N/A | Can UP provide the 60% design as a kmz or CAD file | KPR provided. Updated KMZ will be provided to show electrical and TCE's
2 | P014 | Construction is shown to occur right up to proposed ROW boundary. Please confirm all construction will occur within the ROW boundary and that no TCEs will be required in these locations. | Construction to occur within R/W, TCEs are not required
3 | P019-020
4 | P027-030
5 | P032-033
6 | P026-029 | The proposed ROW from Ellsworth east to the run-around track (~Stas. 157 – 201) has been widened from 110’ (as shown in the previously provided plans dated 3.11.22 and kmz/CAD data) to 145’ (as shown in the 60% plans). This change expands the footprint Jacobs used to conduct our fieldwork and may require additional on-site survey and documentation. Can explain what is driving this expansion? | Addressed by KPR email 6/28/2022
7 | P030-031 | The proposed ROW from Crismon east to the next access road (~Stas. 210 – 222) has been narrowed from a max of 145’ to 100’ feet. The proposed ROW between the access road and Merrill has also been narrowed by 25-35’. These changes do not trigger additional on-site survey or documentation. | Correct; R/W narrowed per negotiations with adjacent landowner
8 | P030-034 | These sheets and the kmz show utility and roadway linework in purple outside of the proposed ROW and TCEs. Please confirm that this work will be done by outside entities and is not part of the PIRATE project. | Confirmed; improvements depicted in purple linework outside of proposed ROW and TCEs will be performed by others and not part of the PIRATE project
9 | P030 | What does the new gray linework represent along the access road shown on the eastern side of this sheet? (Also extends across the next sheet to Merrill Road). | Gray linework depicts grading contours of an adjacent ditch to be constructed by adjacent developers prior to construction of the PIRATE project
10 | P030 | This sheet and the kmz show a ~160-foot-long segment of proposed stormwater line (shown in green in the snippet below) east of Crismon Rd that is outside the proposed ROW and TCEs (note: Crismon TCEs not shown on P030). Can you confirm that this line is part of the PIRATE project? This will likely require an expansion of the APE and additional field survey. | This proposed culvert will be constructed by adjacent developers prior to PIRATE construction (see image to the right)
11 | P031 | This sheet shows removal of one power pole within the proposed ROW, and removal of a segment of OHP that extends outside of the proposed ROW. However, the kmz shows the OHP line to be removed extending farther outside the proposed ROW to a 2nd power pole (a total of ~200’ south of the proposed ROW). Can you confirm what is proposed here – will the line and both poles be removed? This will likely require an expansion of the APE and additional field survey. | The OHP removal will be performed by others and not part of UPRR's scope of work for the PIRATE project.
12 | P032-033 | The proposed ROW from Merrill east to Signal Butte (~Stas. 235 – 261) generally appears to be in the same location or slightly more narrow (~10’). We will review the 60% kmz/CAD data to confirm. | Noted
13 | P033-035 | Both the kmz and the plan sheets show removal of a chain link fence outside the proposed ROW on the northwest corner of the TRW property. Can you confirm that this work is needed for the PIRATE project and clarify why it is not shown within a TCE or the proposed ROW? Will the area between the fence removal and the new track/drainage TCE be used for construction staging, materials stockpiling, or access? This will likely require an expansion of the APE and additional field survey. | Fence removal will only occur within the established proposed ROW or TCEs. The line work reference in the comment is out of date and will be updated. The PIRATE project will not utilize the land between the outdated fence removal and the new drainage TCE.
14 | C012 | Culvert detail sheet still shows extension. | Tracks shown are only for reference to depict potential future track construction performed by others, not to be included with the PIRATE project. This linework will be removed in the Issued-for-Construction plans.
15 | R001 | Can the cross-road detail sheets be revised to show TCEs? | Yes; work areas (same TCE limits shown before) are also now included with the updated KMZ file and can be added to future plan distributions.
16 | R003 | What is the duration of each of the closures? | Construction phasing is currently a work in progress; duration of closures varies based on agency coordination, scope of work at each location, and contractor workforce
17 | R014 | Is the blue box shown a TCE? If so, can dimensions be added? | Per response to Comment 15, TCE's can be shown with the 90% Plans; if needed, see sheet P026 for dimensions
18 | R027 | Will detail sheets be developed for the TRW driveway crossing? Is any detour required, or is all TRW access from Germann Road? | The TRW crossing is not currently going to be constructed as part of the PIRATE project. If it's determined at a later time that TRW crossing will be reconstructed, applicable detail sheets for the TRW driveway/crossing will be developed and included with 90% Plans and detour plans will not be required
19 | GD001 | The wye extension is still shown on this sheet. | Tracks shown are only for reference to depict potential future track construction performed by others, not to be included with the PIRATE project. This linework will be removed in the Issued-for-Construction plans.
20 | GD002 | What is the extension shown at the bottom of the sheet? It is not shown on the 30% plans or the overview sheet. | Tracks shown are only for reference to depict potential future track construction performed by others, not to be included with the PIRATE project. This linework will be removed in the Issued-for-Construction plans.
21 | GD003 | Can a cross-section be provided in this area (see red line below in snip)? It would be helpful to understand how deep the cut would be and what the surface elevation of this area would be following grading. Would it have a single ditch a couple of feet deep or would the entire area be graded? | The existing detention cell is being expanded as shown with the proposed contours (blue linework to the right); cross section is shown in the image below
22
23
24 | E201 | Can UP provide a kmz of the electrical linework? This would useful to compare to other construction, ROW/TCEs, and the APE. | Yes; work areas (same TCE limits shown before) are also now included with the updated KMZ file (to be provided)